## Sheet1
Sprint 2 Backlog - What We're Committing To
Sprint 2: Mar 26 - Apr 16, 2026 ¦ Sprint Goal: ML-powered routing beats static baseline measurably
ID | User Story | Acceptance Criteria | Story Points | Priority | Suggested Area | Owner
PB-13 | As a developer, I want the ML model to predict the best channel per user so that engagement improves over time | - POST /predict: XGBoost returns probability scores per channel - POST /train: retrain on delivery outcomes, evaluate AUC-ROC - GET /model/info: version, metrics, feature importance - 15-feature vector - Different users get different routing | 8 | High | ML Service (Python) | Salvatore
PB-19 | As a developer, I want the worker to call the ML service for adaptive routing | - routing_mode 'adaptive' triggers POST /predict - ML failure gracefully degrades to static routing - routing_decision populated on notifications table - Feature vector recorded with each attempt | 3 | High | Worker (Node) | Zeeya & Dhwalshree
PB-14 | As a developer, I want real-time delivery events in the dashboard | - Worker publishes to Redis pub/sub on delivery events - API subscribes and broadcasts via Socket.IO - Dashboard shows live event feed - Stats cards update in real-time - Auto-reconnect on disconnect | 5 | Medium | Full Stack | Salvatore
PB-15 | As a developer, I want engagement data to feed back into the ML model | - recipient_channel_stats updated after delivery and engagement - Rolling 30d stats: attempts, successes, engagements, avg latency - ML training uses engaged flag as label - Predictions change as data accumulates | 3 | High | Backend + ML | Rhythm & Krish
PB-16 | As a developer, I want fatigue detection so users don't get over-notified | - Track notifications per user per 24h and 7d - Fatigue signals included in ML feature vector - Threshold configurable per tenant | 3 | Medium | Backend | Rhythm & Krish
PB-11 | As a developer, I want rate limiting per tenant | - Redis token bucket per tenant_id - Default: 1000 req/min - 429 Too Many Requests on exceed - X-RateLimit-Limit, Remaining, Reset headers | 3 | High | Backend | Yusif
PB-12 | As a developer, I want CI/CD on every PR | - GitHub Actions: Jest + pytest + TruffleHog - Failing tests block merge - E2E on develop/main merges only | 2 | Medium | DevOps | Yusif
PB-20 | PR self-review checklist (retro action item) | - PULL_REQUEST_TEMPLATE.md in repo - Checklist: no dotenv, no any, no hardcoded creds, field names match contract | 1 | High | Process | Team
PB-21 | Codebase walkthrough session (retro action item) | - 30-min session in week 1 - Cover: env loading, worker flow, dashboard API, shared types - All members attend | 1 | High | Process | Team
SPRINT 2 TOTAL |  |  | 29